## Sheet1
S.no. | Issue Description | Assigned to | Severity | Raised By | Status | Remarks
1 | Product Names are not diaplaying in Flyout cart while adding first time on Endpoint Protection Cloud | Vinita |  |  | Closed | Verified in QA
2 | Error Message: Not removing the previous error when a new error is generted. Case:add 1 user 2 encr -- erro generated add device yearly --- both errors are genarated and page loader is displayed. | Vinita |  |  | Closed | Verified in QA
3 | Remove Functionality: User product not removed from the cart by clicking on remove from flyout. Also, if User and Encryption both are present in the cart then on remove, only encryption is removed. | Vinita |  | Deepali | open | fixed/ Encryption not getting removed in QA
4 | Encryption error message: If there is an error and you again click on 'Add to cart' from the same page then the page is just loading.(page loader is displayed) | Vinita |  | Deepali | open | fixed/Verified in QA
5 | Increase quantity of encryption in Flyout cart on Close Icon: On closing flyout (on close icon) it is generted an error messgae in flyout but it is not visible to the user and flyout disappears | Vinita |  | Deepali | Open | fixed/Verified in QA
6 | Increase quantity of encryption in Flyout cart On checkout button: Click on checkout. Error message generated but On closing flyout (on close icon), The page get greyed out | Vinita |  | Deepali | open | fixed/Verified in QA
7 | Pricing : Prices not updated on + icon on flyout cart for yearly and 3 year subscription (for monthly it is working fine) | Vinita |  |  | closed | not reproducable/ verified in QA
8 | Term Error : User monthly can be added to the cart even if Device yearly is present in the cart. | Vinita |  |  | Closed | fixed/Verified in QA
9 | User and Encryption Term: Different terms of User and Encryption can be added in flyout cart. Case: Add User + Encryption monthly Now add only User yearly. It would be successfully added into the cart with user yearly and encryption monthly | Vinita |  | Deepali | open | not reproducable/ not working in QA
10 | Error message on Server product: On generating error the page is redirected to the home. | Vinita |  |  | closed | fixed/Verified in QA
11 | Previous Error message not removed: Previous error message is not removed from the page. Case: Add monthly device. Add User yearly. It will generate error. Not again add monthly device. The same error message wil be displayed. | Vinita |  | Deepali | open | fixed/Verified in QA
12 | Cart product remove: Cart name and total price are displayed even if we remove all the products from the cart Senario: Add User first. Add Device. Remove User first and then device. The nonly this issue is happening | Vinita |  | Deepali | open | fixed/Verified in QA
13 | SEPC User not getting removed from CC cart even after its deleted from Flyout Cart |  | High | Rishabh | open | fixed/Verified in QA
14 | Should not show any Validation with "Add encryption as text" for ex if SEPC User and Encryption as yearly is there and adding SEPC Device is there monthly andthen validation : |  | High | Rishabh | Open | want to discuss
15 | Loader Not hiding on Add encyption validation on PD page |  | Medium | Rishabh | Open | fixed/Verified in QA
16 | Able to add more products in encryption |  | High | Rishabh | open | fixed/Verified in QA
17 | Price mismatch in cart: After adding encryption, its value can be increased even when user value is less. Updated Value of encryption is going to CC Cart also. |  | High | Shubham | open
18 | Term Mismatch: Add User+Encryption(monthly), again add user+encryption(yearly). Now add only user(term other than yearly), it is getting added. |  | Medium | Shubham | open
19 | Quantity Mismatch: Add User + Encryption. Again add only user(with less quantity). It gets added. |  | Medium | Shubham | open
20 | Product still visible in flyout cart, even when not in CC cart.Case: Add user+device. Remove User first and then device.Again add device. User is visible in Flyout Cart. |  | High | Deepali | open
21 | Manually update the User quantity. Prices show as zero in PD page. |  | High | Virender | open

## screenshot
Defect 15
Defect 16